## Sheet1
Code ID for challenge | Code (Challenge) | Challenge Description | Code ID for strategy | (Mitigation Strategy) | Mitigation Strategy Description | Source | Main Theme | Sub theme
C1 | user story lacks sufficient format to capture relavent information | Insufficiency of the user story format (User story do not convey enough information for software design, especially in large projects) user stories describe system functionalities in terms of the client’s business, they do not really describe the specific implementation details | S1 | Implementation ready user story- delivery story (‘delivery stories’, that extended user stories with a functional specification, high level design and test scenarios) (C1) | ‘delivery stories’, that extended user stories with a functional specification, high level design and test scenarios. (, the delivery story concept provides large projects with something more measurable and concrete than the concept of user stories) Delivery stories do play an important role in (re)prioritization, because they have an associated effort and risk. the information in the delivery stories helps in making sure that the business requirements are technically implementable | WL1 (ScienceDirect) | Requirements Priortization | Artifact based issue
C2 | difficulty in requirements (re)priortization due to inconsensus among customer representatives at inter-iteration level (project level) | (The more people involved in a project, especially the larger the number of client representatives, the higher the risk of contradictory requirements- The disagreement between customer group can affect performance) | S2 | Role involves in requirements priortization at inter-team level: Decision-makers that involves Business Analyst, Tech Lead, Domain Owner, Delivery Team Head, Test Scenario Team Lead and Client's Product Owner who collaboratively make requirements decision. | Decision-makers that involves Business Analyst, Tech Lead, Domain Owner, Delivery Team Head, Test Scenario Team Lead and Client's Product Owner who collaboratively make requirements decision at inter-iteration level; | WL1 (ScienceDirect) | Requirements Priortization | Senior management inability in decision making; Role
C3 | Priortization difficulities due to the volatility (changes from business perspective and a changes from technical perspective), depandence between requirements and specially due to depandent user stories at inter-iteration level | Priortization difficulities due to the volatility (changes from business perspective and a changes from technical perspective), depandence between requirements and specially due to depandent user stories | S3 | criteria for requirements repriortization at inter-iteration level (project level): Requirements depandencies, Volatility, Risk, Effort, and Technical Debt | Requirements depandencies, Volatility, Risk, Effort, and Technical Debt are the priortization criteria that must be used by the vendor's organization in the agile requirements repriortization process | WL1 (ScienceDirect) | Requirements Priortization | Priortization criteria
C4 | Conflicting customer representatives requirements in large scope projects-at program level | Requirements conflicts amongest multiple product owner in large scope projects-at program level | S4 | Common backlog:A single overall backlog can be maintained to guide the team about the overall product features and the interdependencies involved | A single overall backlog can be maintained to guide the team about the overall product features and the interdependencies involved | WL2 (ScienceDirect) | Requirements Priortization | Senior management inability in decision making;
C5 | Testing Inability of cross-functional teams for large scope projects | cross functional teams skills insufficient for testing of large scope projects | S5 | Teams need dedicated testing skills for testing of large scope projects (C5) | Projects with large scope need dedicated testing skills for effective testing of complex modules. | WL2 (ScienceDirect) | Quality assurance | Insufficient competence within the cross-functional teams
C6 | difficulty in the priortization of requirements due to feature depandencies at program level | difficulty in the priortization of requirements due to feature depandencies at program level | S6 | Implementation of strategies to remove requirement issues: Establishment of Frequent communication among customer representatives;introducing the Role of Chief Product Owner | If multiple customer representative,then encourage them to have frequent communication to resolve the requirement issues . Having a single person responsible for deciding on the requirements (chief product owner) helps. | WL2 (ScienceDirect) | Requirements Priortization | Dependencies between requirements
C7 | complexity based Technical inetrdepandency of PB items | higher levels of complexity cause a greater number of technical dependencies between product backlog items | S7 | Role involves in identifying the technical depandencies and priortizing the PB items: Product owner, scrum master (C7) | Scrum masters help the product owner to identify technical depandencies between backlog items and assist in priortizing items | WL3 (ScienceDirect) | Requirements Priortization | Role
C8 | conflicting requirements due to diverse stakeholder communities in large scale development (at portfolio level) | The diverse stakeholder communities in large-scale development communities increase the liklihood of conflicting requirements (at portfolio level) |  |  |  | WL3 (ScienceDirect) | Requirements Priortization | senior management inability in decision making;
C9 | Inadequate Architecture due to new functional requirements | architecture implementation changes precipitated by a new functional requirements may well impact on the work of multiple development teams. (Architecture decisions can have an impact beyond the scope of a particular feature or iteration) | S8 | Architecture implementation as a high-level design (C9) | Practitioners often refer to architecture implementation as high level design | WL3 (ScienceDirect) | non-functional requirements | Impact
C10 | code synchronising problems due to the presence of multiple scrum teams | The presence of multiple scrum teams (whether co-located or geographically distributed) can lead to problems in integrating the code bases under development by different teams. (“They follow their sprint cycle, we follow our sprint cycle. Finally, they match and we take their code base merge into our one and give it to QA as a single release and then it goes into production”) | S9 | Implementation of integration coordination strategy (C10) | scrum masters must adopt and disseminate an integration coodination strategy | WL3 (ScienceDirect) | cooordination and communication | robust-tool infrasturcture
|  |  | S10 | reference architectures are required in order to maintain consistency in design between co-operating developments working on the same development programme; reference architecture defines how the software will meet non-functional requirements, such as performance or security | reference architectures are required in order to maintain consistency in design between co-operating developments working on the same development programme; reference architecture defines how the software will meet non-functional requirements, such as performance or security | WL3 (ScienceDirect) | Architecture | technique
|  |  | S11 | Strategy to improve code quality: establishment of Independent test teams | Independent test teams(third party user acceptance test team) result in higher quality code because developers may reproduce logical errors in both tests and the implemented software | WL3 (ScienceDirect) | Quality assurance | Independent teast team
|  |  | S12 | Implementation of risk assessment for technically complex requirements | Risk assessment is important especially if something is seen as technically very complex; risk assessment should be conducted at the time of defining the minimum viable product; architecture design is used to mitigate any technical complexy identified during the risk assessment process | WL3 (ScienceDirect) | Architecture | technique
|  |  | S13 | Three strategies used for handling issues (defects and feature enhancements): a dedicated maintenance team, a subset of development team members assigned to issue resolution and perodic sprints focusing specially on issues | Three strategies used for handling issues (defects and feature enhancements): a dedicated maintenance team, a subset of development team members assigned to issue resolution and perodic sprints focusing specially on issues | WL3 (ScienceDirect) | Quality assurance | Independent teast team
|  |  | S14 | SoS- a practise to identify and resolve depandencies between teams | Scrum-of-Scrums meeting to identify and resolve dependencies between teams | WL3 (ScienceDirect) | Requirements priortization | Team of team approach
|  |  | S15 | Use of software tools ((Kanban board) to disseminate the progress of features to dispersed team members. | Software tools (Kanban board) to disseminate the progress of features to dispersed team members. | WL3 (ScienceDirect) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C11 | Unpredicatability of the delivery due to lack of coordination over chains of scrum teams | Lack of cordination over chains of scrum teams during the full development lifecycle (A scrum team does not have influencing capabilities on the activities of another scrum team- Scrum teams focus on their on backlog and not on delivery of features, Impact: the lack of influencing capability results in unpredicatability whether a feature gets delivered | S16 | Establish proper coordination mechanism within and over the Scrum teams Scrum of Scrum meetings are typically used to coordinate activities between Scrum teams. (C11) | coordination practices should be deeply embedded within and over the Scrum teams while utilizing all three forms of coordination (mechanistic coordination, organic coordination and cognitive coordination); Deeply embedded coordination will result in better coordination between teams resulting in increased predictability in each of the teams and therefore more delivery predictability. Practise: Scrum of Scrum meetings are typically used to coordinate activities between Scrum teams. | WL4 (ScienceDirect) | cooordination and communication | Misalignment between interdependent scrum teams
C12 | priority mismatches between scrum teams due to conflicting objectives of senior management and their inability in negotiating and decision making | Mismatched backlog priority- priority mismatches between Scrum teams caused by conflicting objectives at the strategic level (senior management is simply not familiar with negotiating and decision making) Impact: impeded delivery of the front to back features | S17 | implementation of strategic decision making strategies, such as (1) using decision analysis tools, (2) acquiring expertise, (3) debiasing judgments, (4) analogical reasoning, (5) taking an outsider view and (6) enhancing the understanding biases of peers (C12), (C6), (C4), (C8) | Priority matching over the front to back chain will be improved, in case the priorities match at the strategic level. Such strategic priority matching requires the implementation of strategic decision making strategies, such as (1) using decision analysis tools, (2) acquiring expertise, (3) debiasing judgments, (4) analogical reasoning, (5) taking an outsider view and (6) enhancing the understanding biases of peers | WL4 (ScienceDirect) | Requirements priortization | senior management inability in negotiating and decision making
C13 | unpredicatability of the delivery due to Misalignment (DoD, sprint duration and test activities) between the codependent Scrum teams | Misalignment between the codependent Scrum teams: An identified misalignment is the definition of done . One team defines ‘done’ as delivered before system testing and another team defines ‘done’ as delivered including system testing. A second identified issue is the misalignment of the start, the finish and duration of the sprints. One Scrum team has a two week cycle and another team has a monthly cycle. A third identified issue is the misalignment of test activities and test results between Scrum teams. Impact: (The misalignment between codependent Scrum teams causes unpredictability and delivery delays) | S18 | (1) A common shared goal and (2) a coordination mechanism improve alignment between Scrum teams. (C13) | (1) A common shared goal and (2) a coordination mechanism improve alignment between Scrum teams. | WL4 (ScienceDirect) | cooordination and communication | Misalignment between interdependent scrum teams
C14 | Lack of feature related information Visibility among teams | lack of information visibility over the prioritized backlogs, the development status of a feature and the underlying functionality. (lack of supporting IT tools that can provide such visibility) Impact:A lack of visibility disables teams to take appropriate action, which leads to uncontrollable impediments later in the sprint. |  |  |  | WL4 (ScienceDirect) | cooordination and communication | Due to communication and collaboration
C15 | Lack of Automation about the tracking of backlog items at inter/intra team level | A lack of automation about the tracking of backlog items. This is largely managed by using Excel sheets. Jira is also used but only limitedly on an intra-team level. |  |  |  | WL4 (ScienceDirect) | cooordination and communication | Due to communication and collaboration
C16 | Unpredictability of the delivery/Difficult to visualize the workflows (feature progress) due to lack of coordination over interdepandent chain of scrum teams | Predictability- unpredictability of whether a feature will be delivered by the interdependent chain of Scrum teams. (In case a feature is not delivered in a sprint, all involved teams need to spend time on that feature in the next sprint. The team that did not deliver needs to manufacture the functionality in the next sprint and the teams that did deliver need to do rework, such as retesting and bug fixing. Impact: cost increase and longer time to market) |  |  |  | WL4 (ScienceDirect) | cooordination and communication | Due to communication and collaboration
C17 | Insufficient understanding of the real end-users need due to lack of involvement of the key stakeholders to the initial backlog creation at pre-development phase/program level | Lack of involvement- The absence of key stakeholders from the process phases where their participation is essential to acquire information and provide input for the development and /or receive feedback. This further caused extra features | S19 | establishing and maintaining effective communication (C17) | All teams should be involved in the development process from in the beginning. In addition, stakeholders should participate in activities requiring their presence. | WL5 (ScienceDirect) | cooordination and communication | Work and improve collaboratively
C18 | Lack of Shared understanding of customer value to team/Lack of customer value to team | Lack of shared understanding- lack of similar understanding of features among team members resulted in increased demands for documenting requirements assigned to them. Otherwise, implemented features might not fullfill customer's expectations. | S20 | Detailed specifications should be written and information should be converged actively. (recommendation of using domain experts communicating daily with distributed teams) (C18) | Detailed specifications should be written and information should be converged actively. (recommendation of using domain experts communicating daily with distributed teams) | WL5 (ScienceDirect) | cooordination and communication | Misalignment between interdependent scrum teams
C19 | defective conveyance of information (feature related) due to to Lack of updated documentation | Outdated information- (Documentation was used as a source of product related information. The initial themes and the user stories were stored in a dedicated Product Backlog tool.In many occasions, documentation was seen as a task of lesser priority and it had to be done later, if at all.); The ProductOwner did not always make his decisions based on the latest information about the particular topic. the documentation was outdated and was missing relevent information. this resulted in defective conveyance of information.) | S21 | Considering documentation, ensuring that it remains up-to-date should be paid attention.This could be achieved by adding documentation related aspects as a part of the acceptance criteria in order to complete a task. (C19) | Considering documentation, ensuring that it remains up-to-date should be paid attention.This could be achieved by adding documentation related aspects as a part of the acceptance criteria in order to complete a task. | WL5 (ScienceDirect) | cooordination and communication | Misalignment between interdependent scrum teams
C20 | inaccessibility of feature related information to team members | Restricted Access to information- Relevant information related to features is not readily available for all parties that need it. | S22 | Provide appropriate access rights to all participants from the beginning of the project (C21) | Provide appropriate access rights to all participants from the beginning of the project | WL5 (ScienceDirect) | cooordination and communication | Work and improve collaboratively
C21 | Limited visibility of interrelated features information implemented by different sites | Scattered information-The information related to the product or project is dispersed in several locations which make it difficult and time-consuming to find. (no uniform approach to update the project wiki- the organization of the wiki caused problems in form of limited visibility to interrelated features implemented by different sites) | S23 | Establish uniform polices to store and document information and follow these guidelines. (C21) | Establish uniform polices to store and document information and follow these guidelines. | WL5 (ScienceDirect) | cooordination and communication | Due to lack of proper requirements traceability mechanism
|  |  | S24 | Establish Role of QR specialist Technical Area Responsible (most experienced and well-respected developers) to manage the internal quality of the subsystem, and technical inter-team coodination. | A special role Technical Area Responsible (most experienced and well-respected developers) might be needed to manage the internal quality of the subsystem, and technical inter-team coodination. | WL6 (ACM) | Quality assurance | Quality assurance experts in teams
C22 | Customer value to team: the product owner needs more reliable collaboration with its business sources to get better understanding and visibility on the success-critical stakeholders in order to share the vision with many development teams | Co-location and Face-to-face collaboration issues (Requirement engineering problems) 1. the product owner needs more reliable collaboration with its business sources to get better understanding and visibility on success-critical stakeholders needs. Then, he has to transfer and share that vision with many development team. 2. Extensive use of communication tools is currently used to simulate co-location but fully intended results cannot always been achieved. | S25 | High management/Steering committee support for PO to identify/analyze/priortize stakeholders requirements (C22) | ( identifying success-critical stakeholders, analyzing and prioritizing their needs require a steering committee not a person.)- High management (steering committee) can support the PO in leading the software development effort by providing him appropriate tools or expertise to support the decision making process. | WL7 (ACM) | cooordination and communication | shared understanding of value
C23 | Difficulties in reaching consensus on the priorties of features due to stakeholders conflicting requirements at program level | conflicting stakeholders’ definitions of success make identification, valuation and prioritization of features very tedious |  |  |  | WL7 (ACM) | Requirements priortization | Senior management inability
C24 | Inability of the customer representative to make appropriate decisions (on requirements priortization) at program level | The product owner has trouble in prioritizing items in the product backlog. Most of the time, he is unable to stop the project and the team continue to produce software until the product backlog is empty. Impact: This situation leads inevitably to unused and/or inconsumable functions.(Increase rework) |  |  |  | WL7 (ACM) | Requirements priortization | Senior management inability
C25 | Requirements depandencies between development teams | Difficulty in managing depandencies with other subsystems and teams | S26 | Implementaion of strategies to manage requirements depandencies: Joint planning workshops, unit-wide retrospective, cross-team testing, cross topic handling via a (temporally) dedicated lead PO and team enablement in task estimation | joint planning workshops, unit-wide retrospective, cross-team testing, cross topic handling via a (temporally) dedicated lead PO and team enablement in task estimation | WL8 (ACM) | Requirements priortization | strategy to Minimize depandencies
C26 | Lack of team autonomy | Teams working on complex or unfamilier tasks are required to coordinate within the team, with other teams(Developers and Testers), and with supporting roles (Line management,Product management, Feature development support, Development support) in the rest of the organization. |  |  |  | WL9 (ACM) | cooordination and communication | Work and improve collaboratively
C27 | difficulty in aligning the security objectives in distributed teams | Alignment of security objectives in a distributed setting; (Team received conflicting request from different security officers) | S27 | Enhance security awerness and knowledge among team members through training and education (C30) | Provide security education and training to employees | WL10 (ACM) | non-functional requirements
C28 | Lack of Automated security testing tools | Integration of low-overhead security testing tools | S28 | Perform security enhancing activites:security code reviews, using security control libraries or the use automated security tests (C28) | Performing security code reviews, using security control libraries or the use automated security tests | WL10 (ACM) | non-functional requirements
C29 | Lack of security documentation | Implementing low overhead security documentation Impact: Ineffective knowledge sharing between security officers and agile team |  |  |  | WL10 (ACM) | non-functional requirements
C30 | Lack of team security awarness and expertrise | Wide variations in security awarness and expertise among team members |  |  |  | W10 (ACM) | non-functional requirements
C31 | Lack of shared understanding of security requirements between security officers and team members | Lack of shared understanding of security requirements between security officers and team members |  |  |  | W10 (ACM) | non-functional requirements
C32 | Lack of common understanding of roles and responsibilities in security activities | Lack of common ommon understanding of roles and responsibilities in security activities |  |  |  | W10 (ACM) | non-functional requirements
C33 | Lack of awerness of business value of security objectives among POs | Product owner involvement and expertise: security awerness and involvement , highly varied among product owners. PO is often not aware enough of the added business value of security action. |  |  |  | W10 (ACM) | non-functional requirements | POs lack of awareness and expertise in NFRs
C34 | Lack of Customer representative access for requirements clarification and feedback | tremendously challenging to verify user stories largely written by different domain experts working in the customer’s organization. (some of the more pressing user needs were not covered in the user stories. user stories we had completely misunderstood, as we had not been able to communicate directly with some of the user groups.) |  |  |  | W11 (ACM) | cooordination and communication | Due to lack of domain knowledge and system limitations
C35 | Difficult to identifies inter-depandencies between requirements | Difficult to identifies inter-depandencies between requirements (difficult to identify functional and/or technical interdepandencies between user stories) |  |  |  | W11 (ACM) | Requirements priortization | Dependencies between requirements
C36 | Inadequate architecture due to change requirements | Inappropriate Architecture when new requirements arise |  |  |  | WL11 (ACM) | non-functional requirements | impact
C37 | Lack of collaboration both inside the software development and the product management | collaboration was clearly lacking both inside the software development and the product management (Features spreading across teams completed late; At the portfolio level Product Managers were concentrating on their own roadmaps whereas products offered to the customers were always combined from several products.) | S29 | Implementation of strategies to Establish closer Communication and collaboration both between the development teams and between the Product managers and Product Owners: SoS meetings supported by RTEs, PO community meeting (C37) | closer collaboration and communication both between the development teams and between the Product Managers and Product Owners (PO)., team having dependencies arrange regular SoS meetings supported by the RTEs. Arrange regular PO community meetings | WL12 (ACM) | cooordination and communication | Learning the RE process
C38 | Missing high level priortization of the product due to Product Managers moving to agile with waterfall mind-set | The high level priortization of the product missing as product managers focused on their own silos | S30 | Training the personnel well in advance, hiring an experienced external consultant to train, advise and support (C38) | Training the personnel well in advance, hiring an experienced external consultant to train, advise and support | WL12 (ACM) | Requirements priortization | Lack of agile mind-set; Strategy-Training
C39 | Difficulty in splitting large and complex requirements in to smaller independent requirements | Product difficult to divide in to reasonable requirements areas as some features touched several areas (its very challenging to implement a feature through one area specific team-many dependencies on other projects or applications ) |  |  |  | WL13 (IEEE) | Requirements priortization | Dependencies between requirements
C40 | inadequate requirements analysis | features and user stories not planned well enough in advance which led unexpected new requirements during implementation |  |  |  | WL13 (IEEE) | cooordination and communication | Work and improve collaboratively
C41 | quality issues such as bugs due to high market pressure on teams to deliver features | team had high market pressure to deliver features which impeded communication in teams.(Teams started to skip and postpone meetings.) Impact: lack of cordination and communication might cause additional challenges such as bugs or solving the same problems simultaneously in different teams. |  |  |  | WL13 (IEEE) | Quality assurance | Pressure on team from management and within their team
C42 | Problem in understanding of requirements to the teams due to lack of proper communication with the POs and the distributed teams | Communication with the POs and the distributed teams was not working well. Especially when explaining the requirements to the teams, (In inter-site communication it was difficult for the APOs to make sure that the requirements were understood correctly) | S31 | Establish Frequent communication with Scrum team(s): • Locate PO close to the development teams; and • arranges requirements and design workshops. (C42) | Enhance communication among teams • Locate PO close to the development teams; and • arranges requirements and design workshops. | WL13 (IEEE) | cooordination and communication | Work and improve collaboratively
C43 | Difficulity in Defining the role of product owner | Difficulity in Defining the role of product owner | S32 | Cross-functional PO teams that shares the responsibilities for technical and business guidance (C43) | APO/PPO team should have some technical background to understand the technical big picture of the product/ or PO role can be divided between two person- system architect aqnd solution architect System architect: Feasibility study, high-level architecture, spliting features in to user stories, communication with scrum teams (s) Solution architect: receiving customer requirements from account managers, communication with system architect | WL14 (IEEE) | Role
C44 | integration and depandencies issues with other subsystems and teams | Integration and Depandency management: 1. services consistently failing to meet the consumer’s requirements and integration points that were poorly tested and failed in system testing. 2. Integration points failed during the sprint review demo because no integration tests were created to validate the services adhered to defined acceptance criteria. | S33 | Implementation of cross-functional teams, self-organized teams, and continious integration and automated test environment to resolve integration and depandency issues. | • Teams must Independently manage their integration points • Employ Test-Driven development techniques and integration tests to define requirements • Create cross-team pairs to implement and integrate services. • Adoption of CI as critical to maintaining a high-quality codebase and limiting the accumulation of integration debt. | WL15 (IEEE) | Quality assurance | Building Continuous integration and test automation
C45 | A gap between the level of detail in their system level features and the detail needed for iteration planning and execution | A gap between the level of detail in their system level features and the detail needed for iteration planning and execution.The use of simple “throw away stories” was insufficient to their challenge of scale. | S34 | Introduce the Role of requirements architect for detailed understanding of the features (C45) | The role of Requirements Architect as part of each development team (The responsibility of each Requirements Architect is to take the high-level features defined by product management and decompose these on a just-in-time basis into the more detailed requirements and stories needed to drive iteration planning and development); Benifit: This new role increased the accuracy of development estimates and improved the collaboration between the development team and product management. | WL16 (IEEE) | Estimation | Balancing planning effort Strategy:Role
C46 | Inaccessibility of customer representatives | inadequate access to product owners |  |  |  | WL16 (IEEE) | cooordination and communication | Due to communication and collaboration
C47 | lack of continious feature integration | Most difficult challenges is staying releasable throughout the development cycle. There are several causes – including late defect discovery and the deferral of major bugs due in part to lack of a continuous build environment | S35 | Implementation of continious integration and test automation-TDD (C47) | Maintaining and improving the continious integration environment; A focus on pulling testing forward in the cycle using TDD practices at both the unit test and acceptance test levels, and increasing the investment in test automation. | WL16 (IEEE) | Quality assurance | Building Continuous integration and test automation
C48 | Unpredicatability of the delivery/Difficult to visualize the workflows (feature progress) due to lack of coordination across teams | difficult for managers to get a complete picture of how the release was progressing. They were unable to tell when particular features were complete as their requirements crossed team boundaries) | S36 | Use of project management tool for Coordinating Multi-Team Development (C48) | Tool support- Using Rally’s application for managing the development lifecycle, BMC is now able to guide the overall release objectives with themes and high-level features. | WL16 (IEEE) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C49 | Code quality issue due to uneven team maturity | code quality challenge- code quality was starting to degenerate as a result of lack of pair-programming. | S37 | Implementation of strategies to enhance code quality: continuous verification and feedback from the business users ; and Pair programming (C49) | Having the client close to the developers not only helps in developing code without making assumptions, it also helps productivity as the feedback loop considerably shortened; Pair Programming was used as a training tool while at other instances it was used a powerful tool to turn ideas into highquality code. | WL17 (IEEE) | Quality assurance | Systematic knowledge management to improve team maturity
C50 | Insufficient availability of the business users (product owner) due to different time zones | developers had no access to the business people to get information relate to features development during their normal business hours unless they worked night shifts |  |  |  | WL17 (IEEE) | cooordination and communication | Due to communication and collaboration
C51 | Lack of requirements documentation | No written documentation |  |  |  | WL17 (IEEE) | cooordination and communication | Due to communication and collaboration
C52 | Lack of visibility of feature progress in distributed teams | No formal procedure to track velocity of the sprints |  |  |  | WL17 (IEEE) | cooordination and communication | Due to communication and collaboration
C53 | Difficulty in writing user stories/cutomer value to team | writing stories to guide development is a challenge, especially in terms of writing stories with the right level of detail and granularity. |  |  |  | WL18 (IEEE) | Estimation; coordination and communication | Lack of maturity with agile method
C54 | Difficulty in tracing the requirements due to lack of requirements documentation | lack of attention to documentation inhibits traceability | S38 | Use of Automation tool (C54) | Powerful toolsset provide extensive and automatic living traceability; impact assessment of changes are easier to identify via the automated tracebility. | WL18 (IEEE) | cooordination and communication | powerful tool-set
C55 | Lack of focus on non-functional requirements/Lack of testing coverage | Testing issues (time consuming regression tests) | S39 | Implementation of continious integration and test automation (C55) | Continuous integration supported by powerful toolset. Automated tests and automatic link to code facilitate easy coverage reporting | WL18 (IEEE) | Quality assurance | Building Continuous integration and test automation
C56 | Retention level of shared vision (Program level, Project level and team level) | (the main problem was the visibility into what PO’s and development teams actually did, which was a result of unclear and shifting priorities from the Marketing and Sales department due to congestion of the development pipeline.) Impact: system completed late; | S40 | Establishment of common backlog at portfolio level | Estabilshment of one common backlog: Listing all projects in priority order in the Paf.com backlog- This helps managers understand what is going on in other departments and the business value of the work. | WL19 (IEEE) | Requirements priortization | Retention level of shared vision
C57 | Inadequate priortization of requirements due to lack of decision making ability of managers | rogue, “business critical” projects induced “under the hood” by some managers | S41 | Use of Web-based management tool to measure and visualizing progress of work and effort left undone in the projects | Use of Web-based management tool to measure and visualizing progress of work and effort left undone in the projects | WL19 (IEEE) | Requirements priortization | senior management inability in negotiating and decision making | Strategy for feature progress: Tool support for coordination and communication
|  |  | S42 | Implementation of strategies to enhance shared understanding of requirements between POs and development teams: Training, Forum for PO | A training package for project management in the context of backlog process could help mitigate the lack of understanding Forum for PO's, where they can interect , learn from each other and solve problems together) | WL19 (IEEE) | Requirements priortization | Strategy: Training
C58 | lack of pre-assignment of features | features allocation/breakdown(the teams have problems to understand which features they were supposed to plan for. it is not practical to have all teams discuss the feature assignments together.) | S43 | Pre-assignment of features (C58) | features should be tentatively pre-assigned. | WL20 (IEEE) | cooordination and communication | Lack of understanding the scale agile practices
C59 | Inadequate priortization of features at team level (lack of advance feature priortization) | Clear priorities for features were missing. The problem became evident especially for Team α whose feature assignments were changed three times during Event A. | S44 | advance feature priortization (C59) | features should be priotized in advance | WL20 (IEEE) | cooordination and communication | Lack of understanding the scale agile practices
C60 | Difficulty in tracing the features | features did not have unique identifiers so that the teams could have easily associated their stories to related features. | S45 | A unique identifiers must be given to features and references from stories to the associated features must be made for tracebility) (C60) | (A unique identifiers must be given to features and references from stories to the associated features must be made for tracebility) | WL20 (IEEE) | cooordination and communication | Lack of tool support
C61 | ignorance of feature depandencies between teams | ignorance of feature depandencies between teams (the teams did not immediately start discussing dependencies between teams. We observed much more interaction between the teams after the teams were instructed to solve dependencies immediately and only defer problems they could not solve to the next status check.) | S46 | depandencies should be resolved immediately when possible (C61) | depandencies should be resolved immediately when possible | WL20 (IEEE) | Requirements priortization | Minimize depandencies
|  |  | S47 | Need to find a balance between feature implementation and quality | Need to find a balance between feature implementation and quality (focus on quality over quantity- if any Scrum team is having defects count above the ceiling level in a particular Sprint, we encourage the team to deliver less features than projected velocity and focus on quality.This includes closing existing defects and working on preventive mechanism to reduce defects for future sprints) | WL21 (IEEE) | Quality assurance | Adopt Stop starting and start finishing mantra
|  |  | S48 | Robust tools infrastructure for transparency and visualization (planning and tracking, test management, requirements management) | Visualization for transparency- Adapt Tools infrasturcture for planning and tracking, test management, requirements management. All these tools are interlinked and have bidirectional linking, like requirement is linked with Themes, Themes are linked with Test cases. | WL21 (IEEE) | cooordination and communication | Robust tools infrastructure for transparency and visualization
|  |  | S49 | early acceptance tests by PO for the closed features to avoid late change request | early acceptance tests by PO for the closed features to avoid late change request | WL21 (IEEE) | estimation | verify by PO
|  |  | S50 | Establishing the Role of architect to manage technical debt | Introducing supportive role i.e. architect to manage technical debts | P21 (IEEE) | Architecture | role
|  |  | S51 | Implementation of continious integration | continious integration-Daily builds, weekly builds (team build, site build, and global build) | WL21 (IEEE) | Quality assurance | Building Continuous integration and test automation
C62 | High Degree of Technical Debt: less focus on quality; and Lack of understanding of the architecture by the new developers | High Degree of Technical Debt (adding new features had the highest priority, and the quality of the underlying system suffered; partly because the overall architecture was not well understood by the new developers. This caused a lot of technical debt) | S52 | Implementation of strategies to remove technical debt: common backlog and supportive roles (subsystem responsibles and architects) (C62) | establishing a common backlog, introducing supportive roles: subsystem responsibles and architects | WL22 (IEEE) | Architecture | role
C63 | Lack of Continuous Integration and Test Automation | Lack of Continuous Integration and Test Automation (integration and testing phase took several weeks before each release. Most of the testing has been manual, as appropriate continuous integration and test automation systems have been missing) | S53 | Building appropriate test environments, training personel on continious integration (“Continuous Integration Road Show") (C63) | Building appropriate test environments, training personel on continious integration (“Continuous Integration Road Show") | WL22 (IEEE) | Quality assurance | Focus on quantity rather than quality
C64 | challenges in defining the product owner role | challenges in defining the product owner role ( Product Owners did not know enough about the new features to be able to answer the questions coming from the team members, instead they were more like messengers.) | S54 | Cross-functional PO teams that shares the responsibilities for technical and business guidance (C64) | setting up a product owner team (PO Cloud comprises all the Product Owners, a portfolio manager, a test manager, and a UX lead.) making it possible to develop clear functional requirements for the teams based upon a deep understanding of the business requirements from the customers point of view. | WL22 (IEEE) | Role | PO role at scaling agile level
C65 | Difficulty in the priortization of requirements due to the Dependencies between backlog items or user stories in particular | The prioritization of requirements is affected by Dependencies between backlog items or user stories in particular Impact: Dependencies in the team backlog dramatically reduce the DoF(Degree of freedom) for prioritization of the team product owner. | S55 | Implementation of strategies to minimize functional dependencies and make them transparent across development teams and business units. (user story mapping or walking skelton, design thinking in combination with user story mapping, backlog management and tracking tools, capture depandencies collaboratively) | 1.) Splitting requirements (“user stories”) in smaller chunks as well as approaches which attempt to generate an overview of the connections between requirements (e.g. user story mapping or walking skeleton) are mechanisms which make requirement dependencies transparent early on. 2.) Creativity techniques in upfront software development stages, such as Design Thinking, in combination with user story mapping helps in creating a more solid product vision. 3.) use backlog management and tracking tools to further improve transparency and coordinate work across multiple teams. 4.) capture dependencies collaboratively-visual analysis and editing functions in real time. | WL23 (Scopus) | Requirements priortization | Strategy: implement strategies to minimize dependencies
C66 | Retention level of shared vision (Program level, Project level and team level) | Hard to estabilish a shared vision with so many stakeholders, leading to disagreements and continued discussions about priorties. (The challenge is if you have a lot of small backlog you are not in control at all. if not everything is visible on the common backlog program and only visible in the XFTs backlog then you maybe having a mismatch.This potential mismatch makes it hard for the program board to establish a prioritization that teams will follow. ) | S56 | Requirements priortization must be done at program level in order make optimal decisions. (C66) | Priortization must be done on the program level in order to make transparency and consistancy between differt backlogs. Thus, if significant information is only available on the teams level and not visible on the program level, priortization decisions cannot be optimal and mismatches will be the consequence | WL24 (Scopus) | Requirements priortization | Retention level of shared vision
C67 | challenging to arrive at long-term estimates, that are applicable for several months,due to a very large size of the product backlog items at that level. Estimation and priortization difficulty due to unclear requirements | it very challenging to arrive at long-term estimates, that are applicable for several months,due to a very large size of the product backlog items at that level. This also made them skeptical about effort estimation in general. |  | Implementation of strategies for ovecoming estimation challenges in large scale agile: Systematic Monitoring: Need to monitor discussions during story estimation. without systematic monitoring of such discussions, they could go on in circles for hours without making significant progress. Estimation based on experience: large-scale agile estimation create a steep learning curve, especially for new team members. Estimation is based learning from past iterations and experience in the team. | Implementation of strategies for ovecoming estimation challenges in large scale agile: Systematic Monitoring: Need to monitor discussions during story estimation. without systematic monitoring of such discussions, they could go on in circles for hours without making significant progress. Estimation based on experience: large-scale agile estimation create a steep learning curve, especially for new team members. Estimation is based learning from past iterations and experience in the team. | WL24 (Scopus) | Estimation | Large-sized requirements ; Strategy: systematic monitoring; Mature teams
C68 | challenging in involvement of teams in long term planning (i.e for priortization and estimation) [how teams should be involved in planning, long and short term] | involvement of teams in long term planning (i.e for priortization and estimation) is quite challenging and it is crucial to find a good process for their involvement) |  | Role involves in long term planning: program leaders, program managers, and to the product line, teams should focus on producing results and cut the lead-time. | a long-term plan is interesting to program leaders, program managers, and to the product line, teams should focus on producing results and cut the lead-time. | WL24 (Scopus) | Estimation | Role
C69 | inter-team communication and coordination overhead due to Inadequate anatomy of features | Communication overhead due to inadequate anatomy of features (The way features are split up and assigned to sprint backlog leads to depeendencies between teams and creates the challenge of inter-team communication and cordination within the larger product portfolio) |  |  |  | WL24 (Scopus) | cooordination and communication | Lack of understanding the scale agile practices
C70 | Lack of shared understanding of security objectives in distributed teams | Alignment of security objectives in a distributed setting: lack of understanding between the information security officers and team members during the system security assessments, several interviewees mentioned that in global systems when multiple security officers (i.e. regional/local/global) had an interest in the security of the system, situations arose in which the team received conflicting requests from different security officers. |  |  |  | WL25 (Scopus) | non-functional requirements
C71 | Lack of common understanding of roles and responsibilities in security activities | developing a common understanding of roles and responsibilities in security activities (the Product Owner is often not aware enough of the added business value for performing certain security actions. In those situations teams rely on the “System Owner to coerce the Product Owner by indicating that it [a certain security feature] is a requirement before going live [with a system]” to be allowed to spend some time on security.) |  |  |  | WL25 (Scopus) | non-functional requirements | Lack of PO knowledge in QR
C72 | Difficulty in coordinating the information related to features due to distributed product area teams | Distributed teams: Product area teams located in different sites | S57 | Use of Electronic Kanban board with team specific swim lanes (C72) | Electronic Kanban board with team specific swim lanes can be useful in this case. | WL26 (Scopus) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C73 | Difficulty in allocating the features across development teams | Feature division: distribution of features across development teams (how the product owner team divides work among development teams) | S58 | Product owner team decides the allocation of prioritized features. Those prioritized features can be displayed on the Kanban board for the teams to pull work items. (C73) | Product owner team decides the allocation of prioritized features. Those prioritized features can be displayed on the Kanban board for the teams to pull work items. | WL26 (Scopus) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C74 | Difficulty in setting WIP limits for development teams at organization level | Defining WIP limits: the setting of WIP limits for development teams ( defining WIP limits for development teams at organization level) | S59 | Defining WIP limit can be resolved by selecting an initial estimate on the basis of a common agreement between development teams. This way a suitable limit can be applied across development teams in the organization. (C74) | Estimate by common agreement between development teams must be provided during the initial phase of defining WIP limits. | WL26 (Scopus) | estimation | Uncertainty about team maturity
C75 | Difficulty in splitting of a large feature into feasible user stories Impact: large features may obstruct the flow of other features on the board. | Large features may obstruct the flow for small features on the Kanban board | S60 | The target size of one feature and the expected duration of implementation by an average team should be clearly communicated. | The target size of one feature and the expected duration of implementation by an average team should be clearly communicated. | WL26 (Scopus) | estimation | Large-sized requirements
C76 | Development teams are in pressure to develop more features due to setting of WIP limit on the program perspective | Product management pushes too many features to the team. If there is a WIP limit based on their perspective, they might force more work | S61 | Limit the number of features coming into the product backlog. These limits should be specified by common agreement of the product owner team and development teams, not by the program. (C76) | Limit the number of features coming into the product backlog. This limit should be set by the product owners and development team representative. | WL26 (Scopus) | estimation | Business pressure
C77 | Difficulty in visualizing and managing the workflows (progress of features) in distributed teams | Teams’ visualization: difficult for a team to know what other teams are doing in the organization | S62 | Use the electronic Kanban board to create different swim lanes in the Development column for the teams. This way, each team can see the other team’s work. (C77) | Use the electronic Kanban board to create different swim lanes in the Development column for the teams. This way, each team can see the other team’s work. | WL26 (Scopus) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C78 | Lack of advance feature preperation | Feature preparation: the preparing of features before forwarding them to teams in the organization | S63 | The product owner team should fine-tune the features, and upcoming features should be visualized on the Kanban board for teams to pull. (C78) | The product owner team should fine-tune the features, and upcoming features should be visualized on the Kanban board for teams to pull. | WL26 (Scopus) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C79 | Lack of details of team-level work at organizational level | Loss of details of team-level work: a possibility when using the organizational Kanban board | S64 | At the organizational level, provide basic requirements (i.e., what is expected from the team). (C79) | At the organizational level, provide basic requirements (i.e., what is expected from the team). | WL26 (Scopus) | estimation | Tool support
C80 | Product management failed to see the WIP limit due to business pressure | Business pressure: pressure to get the release ready can cause people to overlook the specified limits | S65 | Product management or program management must conform to the WIP limit. (C80) | Product management or program management must conform to the WIP limit. | WL26 (Scopus) | estimation | Business pressure
C81 | Difficult to set a fixed limit regarding feature size | Fixed limit regarding feature size: large features require small WIP limits, and the small features require larger WIP limits, thus, it is difficult to set a fixed limit | S66 | A common goal regarding the average implementation time of the feature should be agreed upon. (C81) | A common goal regarding the average implementation time of the feature should be agreed upon. | WL26 (Scopus) | estimation | • Uncertainty about feature size
C82 | Late detection of QRs infeasibility due to inappropriate work coordination and insufficient communication among distributed teams | Late detection of QRs infeasibility: inappropriate work coordination and insufficient communication among distributed teams can result in figuring out too late that a needed QR is infeasible. This may cause expensive refactoring of the software architecture and re-implementing the delivered functions | S67 | Teams cordination and communication practices- -Maintain an assumption wiki-page -Establish preparation team (C82, C83, C84) | Teams cordination and communication practices- -Maintain an assumption wiki-page -Establish preparation team | WL27 (Scopus) | non-functional requirements | impact
C83 | Implementing QRs based on unstated assumptions | Assumptions in inter-team collaboration: teams should establish an unambiguous interaction process to ensure the right implementation of the QRs that they share responsibility for.However, often teams make the assumption that every other team responsible for the implementation of a QR understands its part and will implement it correctly, so the resulting system would demonstrate the quality aspect demanded in the QR specification.this assumption however turns out unrealistic. - |  |  |  | WL27 (Scopus) | Quality assurance | Implementing QRs based on unstated assumptions
C84 | difficult to implement the right QR requirements in a right way due to Reliance on the tact requirements knowledge. | Uneven teams maturity: agile projects Reliance on the tact knowledge especially the knowledge related to architectural significant requirements. they thought experienced developers are more likely to make better architectural decisions than junior developers.however, agile teams usually include mix of experienced and junior developers. they face the challenge of transferring the knowledge from the more experienced to the less experienced team members, that allows both sides to share same knowledge of the system and enhance the overall quality of it by implementing the right QR in a right way. |  |  |  | WL27 (Scopus) | non-functional requirements | Implementing QRs based on unstated assumptions
C85 | Inadequate QRs test specification due to lack of formal modelling of detailed requirements, | Inadequate QRs test specification: QRs are difficult to model and therefore identifying and designing acceptance tests for them may be difficult. Besides, ADMs lack formal modelling of detailed requirements, which makes the process of verifying the QRs more difficult | S68 | Quality Assurance practices -Use automated monitoring tools -Establish QR specialists’ teams -Innovation and Planning Iteration (IP) (C85, C86) | Quality Assurance practices -Use automated monitoring tools -Establish QR specialists’ teams -Innovation and Planning Iteration (IP) | WL27 (Scopus) | non-functional requirements | Lack of standard QRs specification format
C86 | Inadequate architecture due to focus of agile teams on their own component | “We had a software architect responsible for designing the financial component. He overdesigned the system to make it as generic and flexible as possible which resulted in very complex architecture. We could not integrate this component with other parts of the system because we did not understand what goes through it. Therefore, we were forced to rearchitecture the component to be able to integrate it. | S69 | QRs elicitation practices -Establish components teams -Establish preparation team -Reserve part of the sprint for important QRs (C87, C88) | QRs elicitation practices -Establish components teams -Establish preparation team -Reserve part of the sprint for important QRs | WL27 (Scopus) | non-functional requirements | Misunderstanding the architecture drivers
C87 | Lack of clear QRs in a early stage of development | Overlooking sources of QRs: (Most QRs were not identified in advance and were discovered in a later stage. By that time it was very complex to implement them) | S70 | Conceptual practices of QRs -Use automated monitoring tools -Use multiple product backlogs to include requirements of different viewpoints -Maintain an assumption wiki-page -Sprint allocation based on multiple PBs (C89,C90,C91, C92) | Conceptual practices of QRs -Use automated monitoring tools -Use multiple product backlogs to include requirements of different viewpoints -Maintain an assumption wiki-page -Sprint allocation based on multiple PBs | WL27 (Scopus) | non-functional requirements | POs lack of awareness and expertise in NFRs
C88 | Lack of focus of the teams in internal QRs | Lack of QRs visibility: QRs can be broken down into two categories External (e.g. security, performance, availability) and Internal (e.g. maintainability, modifiability, extensibility)-“Internal QRs get attention only when it is really needed and when the system begins to crack” (Customers/POs are not interested in internal QRs) when the pressure on the teams is high to deliver functionalities, you saw that the teams remove invisible QRs from the PB to let FR get higher priority. They thought nobody will care about invisible QRs ”. |  |  |  | WL27 (Scopus) | non-functional requirements | Lack of quality requirements visibility
C89 | Lack of conceptual definition of QRs | Conceptual definition of QRs.:Participants differed in how they defined the nature of QRs and how they should be treated. Participant PA16 explained: “Requirements of quality nature as well as those of functional nature can be placed on the Product backlog as well as the Definition of Done”. others see QRs as constraints on FRs. |  |  |  | WL27 (Scopus) | non-functional requirements | Lack of standard QRs specification format
C90 | Lack of standard QRs specification format | Mixed specification approaches to QRs: unclear conceptual understanding of QRs brings confusion regarding their recording in the DoD or in the user stories.variety of specification formats created confusion of how to express which QRs and how to validate them. |  |  |  | WL27 (Scopus) | non-functional requirements | Lack of standard QRs specification format
C91 | Inadequate architecture due to change in QRs | Unmanaged architecture changes: Changes made to QRs at any time in the development cycle could result in costly changes in the software architecture because the earlier architecture becomes inappropriate for the new QRs |  |  |  | WL27 (Scopus) | non-functional requirements | impact
C92 | Lack of shared understanding of QRs priorties in distributed teams | Misunderstanding the architecture drivers: there is no process to assure that teams maintain the same understanding of QRs’ priorities from architecture standpoint. |  |  |  | WL27 (Scopus) | non-functional requirements | Misunderstanding the architecture drivers
C93 | Difficulty in breaking down the requirements that have direct customer value and can be delivered in small iterations | Customer value to team-s difficult to break down a feature request into small packages that both have customer value and can be delivered in small iterations |  |  |  | WL28 (Scopus) | estimation | Large-sized requirements
C94 | Difficulty in writing the user stories at the scale | How to write meaningful user stories- it is particularly difficult to write user stories that have direct value for the user. Such user stories would typically be too large to be completed and demonstrated in one sprint.. In summary, user stories are hard to write at the scale |  |  |  | WL28 (Scopus) | cooordination and communication | Lack of understanding the scale agile practices
C95 | Lack of awareness about interaction and dependencies of the features between teams | exchange information between the teams, a process which is both difficult and time consuming. Whether developer teams receive already broken down requirements or receive features to break down there are issues regarding synchronisation between teams. Awareness about interaction and dependencies of the features is necessary. |  |  |  | WL28 (Scopus) | cooordination and communication | Misalignment between interdependent scrum teams
C96 | Insufficency of user stories and test cases to capture relavent information for implementation | Tests and user stories are not sufficient:user stories and tests are not sufficient to build and maintain sufficient system understanding. (companies felt a strong need for documentation Especially the need to understand the current system in order to react to new feature requests or system maintenance) |  |  |  | WL28 (Scopus) | Requirements priortization | artifact based issue
C97 | inadequate tool chain of RE | Establishing an agile tool chain:reported that, at the moment, they use traditional tools for requirements management and tools that are aimed at agile development, such as JIRA, for the actual development. These tools are however largely separated and, thus, they felt that in order to be able to perform RE in a more agile way, they would need appropriate tools.. |  |  |  | WL28 (Scopus) | cooordination and communication | Tool support
C98 | Balancing planning effort | Balancing planning effort (balancing the effort spent on planning the requirements and the demands from the development teams for more comprehensive implementation guidance.) Impact: Underestimation of effort of some features and massive over-estimation of others |  |  |  | WL29 (SpringerLink) | estimation | · Balancing planning effort
C99 | Overscoping due to lack of agile mind-set in product management Impact: unexpected scope changes late in the release project | Overscoping caused by pressure from the product management, which led unexpected scope changes late in the release project (Product management requested long-term requirements development plans from the PO team and pressurizes the development to create unrealistic plans.) | S71 | Strategies to deal overscoping: FCS, MMF (C99) | Two approaches: First approach: Improve the predictability of the development by increasing the detail level of FCSs and by increasing the amount of slack in effort estimates. Second approach: Created the concept of a minimum marketable feature, which was the set of epics they could commit to delivering by the next release on a high probability level | WL29 (SpringerLink) | Estimation | Business Pressure
C100 | Insufficient understanding about the development team autonomy (change resistance/lack of agile mind-set in development organization | Insufficient understanding about the development team autonomy (Both managers and developers have difficulties in understanding the additional responsibilities the teams have) The developers expected that they would be given detailed requirements specifications. | S72 | Middle management should empowering the development teams to manage requirements on the development team level level. (C100) | Middle management must have to resist the tendency to command and control development teams. They should empowering the development teams to manage requirements on the development team level. | WL29 (SpringerLink) | Estimation | Balancing planning effort
C101 | Defining the responsibilities of product owners | Defining the role of product owners (High level of technical and business-oriented knowledge is required from the POs who rarely have both.) | S73 | cross-functional product owner team or by splitting the product owner role between multiple people with different responsibilities (C101) | cross-functional product owner team or by splitting the product owner role between multiple people with different responsibilities | WL29 (SpringerLink) | Role | PO role at scaling agile level
C102 | Incapability of cross-functional generalist team in End-to-End feature development | balancing between generalist and specialist team- Cross-functional generalist teams were not capable of developing feature in end-to-end fashion (many components were technically very difficult and required years of experience to completely understand. This had, in several occasions, caused very long lead times) | S74 | Team specialize in business flows (divide the development organization into technical areas based on the structure of the system and allow specialization between those technical areas.) (C102) | Required limited specialization on both the system and team level (divide the development organization into technical areas based on the structure of the system and allow specialization between those technical areas.) | WL29 (SpringerLink)
C103 | Lack of knowledge of the system-level work among development teams | No official way to handle the tasks that is not team specific The tasks included system planning guidance, non feature-specific problem reports, system documentation and external change requests. (the development teams focused on developing features and they lacked knowledge of the system-level work.) | S75 | organizing communities of practice around the system level topics-Establish POs CoP (C103) | product owner teams might be required to coordinate system-level documentation and problem solving in addition to managing the requirements. (organizing communities of practice around the system level topics) | WL29 (SpringerLink)
C104 | Growing technical debt (Neglecting non-functional requirements; Incapability of development teams in long-term technical and architectural planning | Growing technical debt (Less emphasis given to the overall internal quality of the system. The development teams also lacked the skills to do long-term technical and architectural planning. ) | S76 | strategies to overcome technical debt:Explicit architectural and system-level planning may be required to avoid growing technical debt; Establish the role of architect or technical specialist; Organize communities of practice | Explicit architectural and system-level planning may be required to avoid growing technical debt; Organize communities of practice (architect or technical specialist positions may be needed to raise awareness of the problem and to initiate communities of practice to solve it ) | WL29 (SpringerLink) | Quality assurance | Focus on quantity rather than quality
C105 | Growing technical debt/neglect of non-functional functional requirements/focus on quantity over quality | A high degree of technical debt ( adding new features had the highest priority, while the quality of the underlying system suffered) | S77 | Implementation of strategies to overcome technical debt: Establishing a common backlog, investing in system improvements, introducing supportive roles: subsystem responsibles and architects (C105) | Establishing a common backlog, investing in system improvements, introducing supportive roles: subsystem responsibles and architects | WL30 (SpringerLink) | Quality assurance | Focus on quantity rather than quality
C106 | Defining the responsibilities of product owners | challenges in defining the PO role (a few interviewees complained that the POs did not know enough about the new features to be able to answer the team member’s questions. Instead, they were more like messengers.) | S78 | Cross-functional PO team (C106) | Setting up a Product Owner Team, the “PO Cloud” (The PO cloud comprised all POs, a portfolio manager, a test manager, and a user experience lead.) | WL30 (SpringerLink)
C107 | Incapability of cross-functional generalist team in End-to-End feature development | Any team cannot implement any feature (have fully cross-functional and cross-component teams that could implement any feature from the top of the backlog the organization realized that this might never work in practice, as the different components required very specialized knowledge that would take long time to learn.) | S79 | Teams specialize in business flows (C107) | Teams specialize in business flows (teams were starting to specialize in specific business flows, and the idea was to have business flow based backlogs, and each business flow having a few teams. Within these business flows, teams would still be cross-functional and able to develop end-to-end features.) | WL30 (SpringerLink)
C108 | Inadequate requirements management/retention level of high-level features | Backlog challenges (several different backlogs had been in use: an electronic backlog management tool was used for issue tracking, and different stakeholders had their own spreadsheets for managing requirements, features and improvements. This led to poor transparency, and made it impossible to define the cycle time of a single requirement and to see the whole end-to-end flow) | S80 | Establishment of Common backlog for high-level features and improvements at portfolio level (C108) | Common Backlog: common backlog was for high-level features and improvements. every new feature and improvement was to be added to this single backlog. | WL30 (SpringerLink) | Requirements priortization | Retention level of shared vision
C109 | Lack of Continuous Integration and Test Automation | most of the testing was still manual as appropriate CI and test automation systems had not been implemented. | S81 | Building CI teams and appropriate test environments, creating automated tests for legacy code, training personnel on continuous integration as well as build a CI mindset in the whole development organization, e.g., by arranging “CI Roadshows” (C109) | Building CI teams and appropriate test environments, creating automated tests for legacy code, training personnel on continuous integration as well as build a CI mindset in the whole development organization, e.g., by arranging “CI Roadshows” | WL30 (SpringerLink) | Quality assurance | Training personal on continuous integration
C110 | Difficulties in breaking down the requirements that can implement in one release | (ill defined requirements management) (how to break down the requirements small enough to implement within one release by one or a couple of teams. At the time of our interviews, most features still took over one release to implement) |  |  |  | WL30 (SpringerLink) | estimation | large-sized requirements; Uncertainty about feature size
C111 | Basic terms such as features, user story misunderstood by development teams due to Lack of agile training | Lack of Agile Training (the basic terms, such as feature, story or definition of done were not known or understood similarly by all, which is a basic requirement for working together in an agile way. | S82 | Coaching as a substitute for training (C111) | Coaching as a substitute for training | WL30 (SpringerLink) | cooordination and communication | Lack of understanding the scale agile practices
C112 | striking a good balance between agility and stability both at project level and within a development team | (striking a good balance between agility and stability both at project level (degree of commitment in relation to flexibility for late changes) and within a development team (accuracy in effort estimates in relation to level of requirements detailing.) |  |  |  | WL31 (SpringerLink)
C113 | Lack of focus on non-functional requirements | Weak requirements priortization: Requirements are prioritized mainly based on the business value which might cause nonfunctional requirements such as security and scalability would not get incorporated initially. |  |  |  | WL31 (SpringerLink) | non-functional requirements | impact
C114 | Imprecise effort estimate (the development teams underestimate the effort required for development) | weak effort estimates (the development teams underestimate the effort required for development) Impact: Quality issues, delays and customer dissatisfaction are examples of the negative and somewhat expensive effects of overscoping. |  |  |  | WL31 (SpringerLink) | estimation | Uncertainty about feature size
C115 | Difficulties in capturing innovative ideas from development | capturing innovation ideas from the developers |  |  |  | WL31 (SpringerLink) | cooordination and communication | coordination and communication
C116 | Inaccessibility of customers representative | (the customer representative (or proxy) is not always sufficiently available and involved in the development team. ) |  |  |  | WL31 (SpringerLink) | cooordination and communication | Due to communication and collaboration
C117 | Lack of sufficent competance with in cross-functional teamss | ensuring sufficient competence (customer representatives, requirements and testing) |  |  |  | WL31 (SpringerLink) | Quality assurance | Insufficient competence within the cross-functional teams
C118 | Rework and frustration within the development teams due to requirements changes | Weak requirements at start (a lack of a clear requirements picture at the beginning of development. Impact: This had resulted in significant requirements changes during the development with subsequent rework and frustration within the development team.) |  |  |  | WL31 (SpringerLink) | Estimation | Volatile and late requirements changes
C119 | lack of requirements documentation | lack of requirements documentation |  |  |  | WL31 (SpringerLink) | cooordination and communication | coordination and communication
C120 | unplanned technical dependencies during the actual product development due to insufficient planning | The planning challenge (Managers do not plan and allocate tasks to teams in an appropriate way because they do not know much about the code and do not involve in the actual coding- sometimes tasks that should have been assigned to a single team were instead split and assigned to several teams, thereby creating unnecessary dependencies. Insufficient planning leads to unplanned technical dependencies during the actual product development) |  |  |  | WL32 (SpringerLink) | Requirements priortization | senior management inability in negotiating and decision making
C121 | Issue with tasks priortization due to the occurance of unplanned technical depandencies | The task priortization challenge (the task prioritization challenge a result of the planning challenge.When unplanned technical dependencies arise, teams have to update their sprint plan to account for changes in requirements and time-plans. ) Impact: leading to delays and late deliveries. |  |  |  | WL32 (SpringerLink) | requirements priortization | senior management inability in negotiating and decision making
C122 | Lack of knowledge sharing regarding technical depandencies | The knowledge sharing challenge ( Some interviewees do not have the opportunity to say what they want in company meetings (e.g. tasks presentation meetings), because of the multitude of people in the meeting. The interviewees claimed they do not get opportunity to express their burning issues or raise vital questions. – Experienced personnel is involved in difficult tasks and often too busy to be approached. Impact:If knowledge is not properly circulated, communicating technical dependencies will suffer) |  |  |  | WL32 (SpringerLink) | cooordination and communication | Due to communication and collaboration
C123 | Difficulity in maintaining the code quality due to involvement of large number of team members | The code quality challenge (too many people involved in the same code make changes in the code which can end up as conflicts in other teams. hence reducing code quality and creating more technical dependencies) |  |  |  | WL32 (SpringerLink) | Quality assurance | Due to multiple scrum teams
C124 | Integration challenge due to lack of feature progress visibility among development teams | The integration challenge (merging of work packages is a problem because of the many self-organized teams working to deliver an integrated working product to the customers. Our interviewees demonstrated a scenario in which teams develop work packages independently for 2-3 months without knowing what is happening in the main branch. At delivery, teams get conflicts since many changes have been made in the main branch, ) | S83 | strategies to establish effective communication across teams: scrum-of-scrums, continuous integration, open space technology, status reports, virtual architecture teams. | These challenges interact with one another and can lead to a domino effect or vicious circle. If an organization struggles with one challenge, it is likely that the other challenges become problematic as well. This situation can have a significant impact on process and product quality. Our recommendations focus on improving planning and knowledge sharing (with practices such as scrum-of-scrums, continuous integration, open space technology) to break the vicious circle, and to reestablish effective communication across teams. | WL32 (SpringerLink) | cooordination and communication | Introduce knowledge transfer sessions
C125 | Difficulity in maintaining the code quality due to pressure on programmers both from from management and from within their team | loss of quality in code due to pressure on teams (Programmers complained about the pressure both from management and from with in their team) | S84 | Strategies to coordinate work / communicate requirements to scrum teams: Form Special product teams- Scrum-of-Scrum and supervisory product owner team | To co-ordinate the work of multiple Scrum teams and to communicate the requirements via team product backlogs, various approaches were combined. Special product teams were formed for this purpose. These teams can be regarded as both a permanent Scrum of Scrums and a supervisory product owner. | WL33 (SpringerLink) | Quality assurance | Pressure on team from management and within their team
C126 | difficult to divide a product into independent requirement areas | The role of software architecture (high-level design) was not yet well understood.This led to increased dependencies among products and components, e. g. because componentization was weak and code reuse was highly valued. | S85 | Undone Department of the organization included Architectural Team, Support Team, which removed impediments that could not be resolved by development teams, and expert Lean team | Undone Department of the organization included Architectural Team, Support Team, which removed impediments that could not be resolved by development teams, and expert Lean team | WL33 (SpringerLink) | Architecture | Role
C127 | Lack of shared undersatnding of development goals between the product management and between the product management and development teams | Communication among product management, software architects, development teams, and quality assurance was not strong enough to ensure a common understanding of development goals. | S86 | Form Special team that provide education on software architecture for developers, software architects, and product management. (C126, C127) | To overcome both problems a team was formed to provide education on software architecture for developers, software architects, and product management. | WL33 (SpringerLink) | cooordination and communication | shared understanding of value
C128 | Lack of teamwork | teamwork was hindered (Team members thought that Scrum was introduced to increase efficiency and substitutability of programmers. Also, they thought that flatter management hierarchy offered fewer career opportunities. Hence, people tried to be more visible and competitive) |  |  |  | WL33 (SpringerLink) | cooordination and communication | Lack of understanding the scale agile practices
C129 | difficulty in achieving the shared undersatnding of development goals between the product management and between the product management and development teams | having multiple on-site customers increases the risk of failure because of the challenge of estabilishing a common understanding among all customer representatives (challenge of alignment between the on-site customer representatives and between on-site customers and development team) | S87 | open and transparent dialogue and cross group communication as essential for aligning the different stakeholder groups. (C129) | open and transparent dialogue and cross group communication as essential for aligning the different stakeholder groups. | WL34 (SpringerLink) | cooordination and communication | shared understanding of value
C130 | Neglance of non-functional requirements at program level | Performance neglected for the main part of the programme but received a significant attention in the final stages.This triggered some re-work for the architecture team | S88 | Additional roles (technical architects, and functional architects) and arenas (SoS, Meta scrum) are required in order to manage depandencies between teams. | Additional roles (technical architects, and functional architects) and arenas (SoS, Meta scrum) are required in order to manage depandencies between teams. | WL34 (SpringerLink) | non-functional requirements | impact
C131 | Lack of focus on code quality due to pressure on teams to deliver functionality | Technical debt accumlate due to the pressure to deliver functionality (functionality was given priority over refactoring) | S89 | establish a common product backlog as a master plan and maintain in an issue tracker (gives a better overview of depandencies between stories and enabled a more efficient development path) | establish a common product backlog as a master plan and maintain in an issue tracker (gives a better overview of depandencies between stories and enabled a more efficient development path) | WL34 (SpringerLink) | Quality assurance | Focus on quantity rather than quality
C132 | Lack of maturity of the teams with the method | feature VS story concept not clear |  |  |  | WL35 (SpringerLink) | cooordination and communication | Lack of understanding the scale agile practices
C133 | Imprecise effort estimate | the initial scope (in the 1st BIP and also the 2nd) was perhaps an order of magnitude bigger, than what R&D could deliver in the expected timeframe. | S90 | Implementation of strategies to enhance quality: continious integration and Test automation | Paying attention to Quality and the engineering practices like Continuous Integration and Test Automation is essential. • Every bug found invokes adding a new test case to the Test Automation suite • Never sacrifice quality • No extra hardening outside of sprints, every sprint results in a customer beta | WL35 (SpringerLink) | Quality assurance | Building Continuous integration and test automation
C134 | Neglance of non-functional requirements | Sometimes product managers are not fully aware of the non-functional requirements. Demnostrations do not demnostarte the NFRs.this can come as a defect in large-scale testing . There is no denial that NFRs like scalability are ignored in agile projects. |  |  |  | WL36 (SpringerLink) | non-functional requirements | POs lack of awareness and expertise in NFRs
C135 | Inadequate architecture due to requirements change | Requirements stability (changes in NFRs caused refactoring of design and code) |  |  |  | WL36 (SpringerLink) | non-functional requirements | impact
C136 | Integration issue due to lack of feature progress visibility in multiple teams | Integration (Other teams change something which was not available to us for testing and that has cost us the defect. ) |  |  |  | WL36 (SpringerLink) | cooordination and communication | Due to communication and collaboration
C137 | Overestimations due to lack of team maturity | Estimation: It depends how mature the team is. There are overestimations because of which the team needs to stretch. (If I didn’t estimate the size of the feature or predict the feature to be unstable then my schedule gets extended. ) |  |  |  | WL36 (SpringerLink) | Estimation | Uncertainty about team maturity
C138 | Lack of visibility of requirements changes among scrum teams | Re-implementation due to bugs or changes from customer is not updated to the release backlog. Some scrum teams may not be aware of the changes. |  |  |  | WL36 (SpringerLink) | cooordination and communication | Due to communication and collaboration
C139 | Difficulty in breaking down the requirements across different phases of the project | How to split the requirements, how to phase them across different phases of the project, I would say, continues to be a challenge. |  |  |  | WL36 (SpringerLink) | cooordination and communication | Lack of understanding the scale agile practices
C140 | Lack of shared understanding of requirements between product managers and developers | Perspective of developers and product managers differ sometimes due to poor understanding of requirements. What we consider done is not considered done by product manager sometimes |  |  |  | WL36 (SpringerLink) | cooordination and communication | shared understanding of value
C141 | lack of external testing at sprint level | Testing completeness: (The external testing is only done at the end of a release and not after each sprint. It might reveal that the algorithm is not fully tuned to real world cases. Another 2 or 3 weeks are spent on adjusting the product. ) Impact: Underestimated effort for bug-fixing |  |  |  | WL36 (SpringerLink) | Quality assurance | Lack of tool
C142 | System completed late due to Reliance on tacit requirements knowledge | When project members leave] the management does not have budget for additional head count. In that case the deadline is increased or the scope reduced |  |  |  | WL36 (SpringerLink) | estimation | Uncertainty about team maturity
C143 | Defining the responsibilities of product owners | Defining the role of Product Owner (PO) | S91 | Cross-functional PO teams that shares the responsibilities for technical and business guidance (C143) | The explict formation of a PO team with the full range of business and technical skills is required. (client-side PO functions-groom, priortiser, communicator, intermediary, and traveller) (Production-side PO functions- the governer, technical architect, risk assessor, and release master) | WL37 (SpringerLink) | role | role of PO at scaling level
C144 | Difficulty in user story estimation due to lack of clear understanding of the skills of the offshore team | User story estimation (Establishing correct user story estimates as onshore team does not have clear understanding of the skills of the offshore team) | S92 | By doing the planning poker activity together all team members will get a better understanding of each others skills (C144) | By doing the planning poker activity together all team members will get a better understanding of each others skills | WL38 (SpringerLink) | estimation | Distributed team
C145 | Difficulty in getting the project's main objective in distributed team members | Objective and core functional requirements (Getting the main objective and core functional requirements of the project clear to all the team members located at different sites) | S93 | Project Charter (C145) | having a project charter document written at the start of the project, will give all the team members a clear understanding of the projects objective and core functional requirements | WL38 (SpringerLink) | cooordination and communication | due to cooordination and communication
C146 | Misunderstanding of requirements due to cultural values and language | Misunderstanding of requirements (Differences in cultural values and language can cause misunderstanding of requirements) | S94 | Collective project planning, Asynchronous information transfer, Synchronous communication (C146) | Since the whole team will be part of the planning activity, the chances of misunderstanding a requirement will be reduced; In case of any misunderstanding, the team members can communicate with each other using asynchronous tools; For a real time response to any misunderstanding, the team members can use synchronous methods for communication | WL38 (SpringerLink) | cooordination and communication | Due to language constraints and cultural values
C147 | Vague requirements | Vague requirements (As at the beginning of the project the client is not sure of all the requirements, which can result in vague requirements, which need to be later clarified to the teams who are not on-site) | S95 | team members should visit offshore team members and vice versa to discuss the requirements in order to avoid defects (C147) | To clarify vague requirements, onshore team members should visit offshore team members and vice versa to discuss the requirements in order to avoid defects | WL38 (SpringerLink) | cooordination and communication | Introduce knowledge transfer sessions
C148 | Difficulty in communicating the requirements changes in distributed teams | Changes in the requirements (Changes in the requirements, needs to be communicated to all the distributed teams. Any mistake in recording the change can cause problems in the development of the system) | S96 | Use Global Scrum Board (C148) | Any change in the requirements will be updated on the global scrum board, which is accessible by all team members in real time. | WL38 (SpringerLink) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C149 | inconsistencies in the work done and documented user stories due to distributed teams | Inconsistencies ( As the project is being developed at different locations, there can be inconsistencies in the work done and documented user stories) | S97 | Use Central Code Repository (C149) | To avoid any inconsistency between the work done and the user stories, all the team members use a central code repository, which is accessible by the whole team | WL38 (SpringerLink) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C150 | Difficulty in maintaining bidirectional tracebility of requirements in distributed teams | Bidirectional traceability of requirements (Maintaining bidirectional traceability of requirements across different sites is difficult as each site is working on different use stories) | S98 | Central code repository; Global scrum board (C150) | Central code repository; Global scrum board | WL38 (SpringerLink) | cooordination and communication | Robust tools infrastructure for transparency and visualization
C151 | Lack of requirements documentation | lack of formal document for requirements (Lack of formal requirements was identified as the barrier for the project teams that faced challenges in terms of capturing business requirements in an easy and effective way) |  |  |  | WL39 (SpringerLink) | cooordination and communication | Lack of tools support
C152 | Inadequate team structure/barrier between generalist against specialist behaviour in the technical team | Inadequate team structure (project faced a barrier between generalist against specialist behaviour in the technical team-In this project even with performance testing training available test team avoided to execute performance testing because they were primarily functional testers.) |  |  |  | WL39 (SpringerLink)
C153 | Quality issues due to lack of team maturity | Quality issues due to lack of team maturity (a lack of team maturity in agile practices impacted team capacity evaluation. Instead of cutting a sprint scope and postponing the work till the following sprint, the testing team decided to test the outcome using the overtime to deliver the goal. That resulted in defects and test scenarios not mapped into acceptance criteria. ) | S99 | Strategies to enhance quality: Automated tests, continious integration, code coverage tools, and assign testers and developers to work together (C153) | Increase testing practices, automated if possible (increase the use of automated tests and practices like continious integration);static audit tools and code coverage tools can help the team to keep track of source code and code quality | WL39 (SpringerLink) | Quality assurance | Lack of team maturity
C154 | Difficulities on estimating story points at project level | Difficulities on estimating story points | S100 | Use three different roles while estimating, like developer, tester, and analyst; for every estimation game, define one person responsible to be the local leader (C154) | Use different roles while estimating, like developer, tester, and analyst; for every estimation game, define one person responsible to be the local leader | WL39 (SpringerLink) | estimation | role
|  |  | S101 | Strategies to Avoid late discovery of integration issues and Improve system level understanding and testing in the project: continious integration and single main truck in CM system | Continious integration- an automated build process with optional regression tests and failure re-ports Single main trunk in CM system-This forces the integration issues to arise, and be fixed, early on | WL40 (SpringerLink | Quality assurance | Building Continuous integration and test automation
C155 | Low focus on non-functional requirements at iteration level | quality testing in the LSV (latest system versions) :quality testing in the LSV takes too much time- the reason being that there was a lack of powerful hardware available to developers to do quality testing earlier.; the project cycles are too short to squeeze everything into the project; and there is a lack of independent verification for basic and component testing. | S102 | Implementation of strategies to enhance test coverage- TDD, Automated testing (C155) | by implementing test-driven development or increase the degree of automated testing to speed up the testing process. | WL41 (SpringerLink) | Quality assurance | Building Continuous integration and test automation
C156 | Imprecise effort estimate | constant over-committing,-Teams failed to deliver half of promised scope with velocity 0.5 in compare to original optimistic estimates |  |  |  | WL42 (SpringerLink) | estimation | large-sized requirements
C157 | Team frustration and technical debt due to pressure on team from management | Pressure on team by management led to many negative consequences like technical debt, and team frustration. |  |  |  | WL42 (SpringerLink) | Quality assurance | Pressure on team from management and within their team
C158 | Difficulity in creating and maintaining the priority list | The priority list is essential in the company’s model to work and is hard to create and maintain |  |  |  | WL43 (SpringerLink) | requirements priortization | requirements depandencies
C159 | missing detailed dependencies due to Lack of focus on design | detailed dependencies are not discovered on detailed level due to lack of focus on design. |  |  |  | WL43 (SpringerLink) | requirements priortization | requirements depandencies
C160 | challenging to estimate large projects | Scale of project makes it difficult to estimate and plan | S103 | Strategies to minimimise underestimation:consider factors that could add delay to the project (e.g. PC size, team maturity etc.), to reduce over-optimism bias | to minimise underestimation, consider factors that could add delay to the project (e.g. PC size, team maturity etc.), to reduce over-optimism bias | WL44 (SpringerLink) | estimation | large-sized requirements, team maturity
C161 | effort overruns due to no of sites; no of stakeholders, size and complexity of legacy code | Scale includes many factors beyond Product Customization (PC): including no of sites; no of stakeholders, size and complexity of legacy code | S104 | Role that must involve in the estimation process: system Mgrs, PM, architects, TL | involve all concerned stakeholders (e.g. system Mgrs, PM, architects, TL) in the estimation process. SW Architects understanding of the product's architecture allows them to perform an impact analysis of new reqmts/tasks at the system level. | WL44 (SpringerLink) | estimation | role
C162 | estimation inaccuracy due to lack of well-defined requirements and frequently changing requirements | requirements related issues such as lack of detail and changes in reqmts | S105 | Re-estimation at the analysis stage improves the effort estimates.Refined estimates help PMgrs in monitoring progress on tasks | Re-estimation at the analysis stage improves the effort estimates. More is known about the reqmts and assigned team. Refined estimates help PMgrs in monitoring progress on tasks | WL44 (SpringerLink) | estimation | Volatile and late requirements changes
C163 | effort overruns due to lack of expertise of newly on-boarded teams | lack of expertise of newly-onboarded team results in delays | S106 | Take into account that: large sized reqmts/taks are more likely to incur large effort overrun | Take into account that: large sized reqmts/taks are more likely to incur large effort overrun | WL44 (SpringerLink) | estimation | team maturity
C164 | effort overruns due to dependencies (such as for code reviews) on specific human resources (e.g. product architects) | dependencies (such as for code reviews) on specific human resources (e.g. product architects) introduces delays | S107 | mature teams should be involved in the effort estimation process as they have architectural knowledge and expertise | mature teams should be involved in the effort estimation process as they have architectural knowledge and expertise | WL44 (SpringerLink) | estimation | team maturity
C165 | underestimating the technical complexity of large requirements | underestimating the technical complexity of some large PCs | S108 | Take into account that: less mature teams need more time to complete the tasks and hence more likely to incur effort overruns | Take into account that: less mature teams need more time to complete the tasks and hence more likely to incur effort overruns | WL44 (SpringerLink) | estimation | team maturity
C166 | challenging to estimate large projects due to their inherent complexity | more challenging to estimate large projects due to their inherent complexity | S109 | Take into account that: multi-site development, wherein geographically distributed teams collaboratively work on a task, exacerbates underestimation bias | Take into account that: multi-site development, wherein geographically distributed teams collaboratively work on a task, exacerbates underestimation bias | WL44 (SpringerLink) | estimation | distributed team
C167 | Instability in requirements | late changes in reqmts after quotation stage - more common for high priority PCs | S110 | Monitor and manage the estimation process to avoid lengthy discussions without any progress | Monitor and manage the estimation process to avoid lengthy discussions without any progress | WL44 (SpringerLink) | estimation | monitoring
C168 | effort overruns due to communication and coordination difficulties in multi-site dev't, global barriers related to time, distance and culture | inherent communication and coordination difficulties in multi-site dev't, global barriers related to time, distance and culture - result in delays due to extra work | S111 | solid mentoring support provided by product architects is essential for newly on-boarded teams | solid mentoring support provided by product architects is essential for newly on-boarded teams | WL44 (SpringerLink) | estimation | mentoring support
C169 | A special role/team is needed for Architectural planning in large scale agile programmes | A special role/team is needed for Architectural planning in large scale agile programmes | S112 | Implementation of strategies to architecture development in large scale agile programmes: design/architecture community of practice, chief architect, technical service team, technical consulting team (C169) | four approaches to architecture development in large-scale agile programmes: community of practice, chief architect, technical service team, technical consulting team. In the design/architecture community of practice model, a self-selecting small group of specialists representing each team work together to derive the architecture. The chief architect approach, in contrast, uses a technically skilled individual to coordinate the architecture needs of the cooperating teams. In development programmes with complex architecture needs, a specialist team is formed called the technical service team. The technical service team provides architecture development services to the feature teams. Some organisations impose corporate architecture governance on teams across development programmes, in such cases a technical consulting team can provide architecture support to feature teams combining the community of practice or chief architect and technical services team models | WL45 (SpringerLink) | Architecture | Role
C170 | code quality loss due to pressure on teams form management | (code quality loss due to pressure on teams form management | S113 | Strategies to enhance to code quality: Building an appropriate test environment and training personal on continious integration; quality assurance experts in the teams; (C170) | Building an appropriate test environment and training personal on continious integration; quality assurance experts in the teams; | WL46 (Snowballing) | Quality assurance | Building Continuous integration and test automation ;Training
C171 | Lack of teamwork due to too much specialization in the development teams | The company let the teams create their entire development process and select their tools and technologies because there was no need to unify the processe as the development teams almost did not inter-act among themselves. the company soon realized that the development teams did not manage their processes properly.Technical debt piled up, | S114 | Implementation of strategies to enhance knowledge sharing within and across teams: using workshops or establishing CoPs (C171) | Establishing a process for knowledge sharing between team members early,for example,using workshops or establishing CoPs.In later stages,there is the risk that team members might consider their knowledge too important to share it. | WL46 (Snowballing) | cooordination and communication | Introduce knowledge transfer sessions
C172 | Issue with Integrating the previous and non-agile parts of organization | Integrating the previous and non-agile parts of organization |  |  |  | WL46 (Snowballing) | Quality assurance | lack of tool
C173 | Difficult to divide the requirements in independent product areas | Difficult to divide the requirements in independent product areas |  |  |  | WL46 (Snowballing) | cooordination and communication | Lack of understanding the scale agile practices
C174 | Neglecting technical considerations during priortization of user stories | Incorrect prioritization of User Stories (User Stories were usually prioritized without taking the technical considerations into account. if a critical interdependency among User Stories was found, it might have required significant re-factoring with consequences for the whole structure of the software) | S115 | Organize feature analysis workshops that invloves all the main members of the project-developers, architects (C174) | The architects and developers should be involved in prioritizing User Stories.(“Feature Analysis Workshops” in which all the main members of the project participated for understanding and prioritizing User Stories) | WL47 (Snowballing) | requirements priortization | Ignorance of technical requirements strategy:Role
C175 | Lack of time and motivation in agile teams to consider design choices | Lack of time and motivation to consider design choices: teams were forced to focus on a limited number of solutions to achieve the required features within time and budget. Main risk: 1. No time for careful design during iterations 2. No considerations for alterative, potentially better design choices can be missed | S116 | Two approaches 1. Sprint zero: have an iteration for doing architecturally focused work. Such iteration can be combined with the “Feature Analysis Workshop (FAW)” 2.Time allocated in each iteration for developers to think about different design choices in order to identify the most appropriate design choice. (C175) | Two approaches 1. Sprint zero: have an iteration for doing architecturally focused work. Such iteration can be combined with the “Feature Analysis Workshop (FAW)” 2.Time allocated in each iteration for developers to think about different design choices in order to identify the most appropriate design choice. | WL47 (Snowballing) | Architecture | Technique:FAW, Buffer time
C176 | Difficulty in coodinating the information (features related) in distributed teams | Realizing a requirement needed the participation takt teams based in different locations and in different time zones. As a result, seeking and getting clarifications took more time, which made it difficult to meet the takt deadlines. | S117 | Introduce knowledge transfer session (C176) | Knowledge transfer sessions introduced. Result: No synchronization issues. | WL48 (Snowballing) | cooordination and communication | Due to communication and collaboration strategy: knowledge transfer session introduced
C177 | Overscoping: Difficult to complete the large and complex requirements in a single sprint | Large and complex requirements that could not be completed in a single takt. | S118 | Applied the principles of user-centered design to split large and complex requirements in to smaller requirements that could be completed with-in one takt. (C177) | Split large and complex requirements into smaller requirements that could be completed with-in one takt. (Applied the principles of user-centered design to split large and complex requirements in to smaller requirements that could be completed with-in one takt.) | WL48 (Snowballing) | estimation | Lack of maturity with agile method
C178 | Prioritization of feature requirements over testing and fixing defects (managing technical debt)/ensuring code quality | Prioritization of requirements over testing and fixing defects (more time was taken towards implementing requirements, the time available to complete tests was inadequate. Increasingly, the requirements developed in a takt were not tested sufficiently, and increasingly, a number of tests were being deferred to subsequent takts and in some cases even to the hardening takts.). | S119 | Stop starting and start finishing mantra adopted. -Made it mandatory that code satisfied the defined completion criteria. -Enforced the defined release criteria for each component. (C178) | Stop starting and start finishing mantra adopted. -Made it mandatory that code satisfied the defined completion criteria. -Enforced the defined release criteria for each component. Result: Early detection of defects. Sufficient time for analysis and proper fixing. Wait-time to get a testable build reduced to zero. Number of legacy defects always in control | WL48 (Snowballing) | Quality assurance | Stop starting and start finishing mantra adopted
C179 | integration issue due lack of continious integration | In some cases, the integration was only possible in the final development takt. As a result, integration-related issues were identified towards end of the development takts. The late integration of the code developed by the independent takt teams also resulted in collaboration-related issues.) | S120 | Adopt Continious integration (C179) | Adopt Continious integration | WL48 (Snowballing) | Quality assurance | Building Continuous integration and test automation
C180 | neglance of non-functional requirements in the early stages of realizing requirements-portfolio level | Non-functional requirements not getting adequate focus in the early stages of realizing a requirement. | S121 | Automated the stress and load monitoring test cases. (C180) | Automated the stress and load monitoring test cases. | WL48 (Snowballing) | non-functional requirements | non-functional requirements
C181 | Lack of focus on overall project goals among team members | the team members were more focused on achieving individual goals by completing tasks assigned to them, rather than focusing on achieving the takt team goals and the overall project goals. | S122 | Empowered the team members to pick the requirements based on their expertise. Set team goals and laid greater emphasis on team achievement over individual achievement. (C181) | Empowered the team members to pick the requirements based on their expertise. Set team goals and laid greater emphasis on team achievement over individual achievement. Result:Team goals resulted in greater collaboration and in many cases developers willingly supported the other team members to complete their tasks. | WL48 (Snowballing)
C182 | Insufficient build and test automation | Insufficient build and test automation | S123 | Automated the setup of different environments. Optimized automated test cases to avoid unnecessary wait times adapted the test suites to enable parallel execution. Set up multiple large configurations. (C182) | Automated the setup of different environments. Optimized automated test cases to avoid unnecessary wait times adapted the test suites to enable parallel execution. Set up multiple large configurations. | WL48 (Snowballing) | Quality assurance | Building Continuous integration and test automation
C183 | Finding the right balance between architectural improvements and business value/ lack of focus on architectural and technical qualities | Architectural and technical qualities are given low priority (a stronger focus on architectural and technical qualities is recognized as diametrical to concerns such as the time pressure of the project, the product owner’s field of expertise, and the agile focus on value for customer. The perception is nevertheless, that technical qualities should receive more attention.) | S124 | seprate backlog for technical improvement tasks; enhance test coverage (C183) | 1: Maintain a designated backlog of technical improvement tasks along with incentives to solve these tasks (one item in the backlog might be to designate effort to optimize the use of the test execution tool). 2: Conduct more systematic tests of technical qualities at the sprint checkpoints. | WL49 (Snowballing) | Architecture | technique
C183 | uncertainty in effort estimation due to late changes in requirements | Volatile and late requirements from external parties (volatile and late requirements introduce uncertainty in effort estimates, and are perceived to be a direct cause of delays. | S125 | 2: Document and convey the quality of the process that led to estimates and uncertainty analyses. 3: Reevaluate time scope and level of detail for estimates. 4: Ensure that people with competence on the software solution participate in estimation (C183) | 2: Document and convey the quality of the process that led to estimates and uncertainty analyses. 3: Reevaluate time scope and level of detail for estimates. 4: Ensure that people with competence on the software solution participate in estimation | WL49 (Snowballing) | estimation | Volatile and late requirements changes
C184 | Lack of shared vision for the end product among development teams | Lack of shared vision for the end product ( Without shared vision, there are concerns that redundant work is being done, that code will have to be withdrawn, and that the system will eventually not fully satisfy the user’s needs) | S126 | Implied starting points for improvement: 1: Clarify how and by whom the overall solution is envisioned. 2: Allocate time to describe and communicate vision (C184) | Implied starting points for improvement: 1: Clarify how and by whom the overall solution is envisioned. 2: Allocate time to describe and communicate vision | WL49 (Snowballing) | cooordination and communication | shared understanding of value
C186 | integration issues and dependencies with other subsystems and teams | Excessive dependencies within the system (challenging to handle interdependencies between code that is developed in parallel expensive corrections to incompatible code parts had to be done, and in a few cases, teams were unknowingly developing code for the same features. The problem of interdependencies in newly developed code has also led to challenges with configuring integration test environments and test data | S127 | Implied starting points for improvement: 1: Identify dependencies between product queue elements at an early stage of release planning. 2: Clarify the responsibilities for configuring test data. 3: Assess the need for broader knowledge of the business domain and the solution in different parts of the project (C186) | Implied starting points for improvement: 1: Identify dependencies between product queue elements at an early stage of release planning. 2: Clarify the responsibilities for configuring test data. 3: Assess the need for broader knowledge of the business domain and the solution in different parts of the project | WL49 (Snowballing) | Requirements priortization | requirements depandencies